# CloudResearch — Start-Here Guide (Pixel-10 friendly, ADD-friendly)

Owner: Yasir A. Malik

Purpose: Get CloudResearch from zero to soft-launch-ready by Wed Jun 24.

Companion: 03_Recruitment_and_Pilot/YMalik_CloudResearch_Launch_Draft_READY_2026-06-01.docx (already in repo — your study-listing, screening, and quality filters live there)

One task at a time. Do step N. Stop. Come back. Do step N+1. Don't read ahead.

## Before you start — what you need in hand

[ ] Anonymous Qualtrics link (created once the Qualtrics build is published — Tue Jun 23 in the plan)

[ ] A funding source — debit/credit card or wire. CloudResearch is prepaid (you load money first, then pay per response).

[ ] IRB protocol number — IRB-25-0462 — keep it copy-paste handy.

[ ] Compensation amount — $6.00 USD per completed response (within IRB-approved fixed compensation language).

[ ] Target sample size — soft-launch 15, full launch 60–80.

## Step 1 — Create the account (5 minutes)

On your Pixel, open Chrome → go to `connect.cloudresearch.com`

Tap Sign Up → choose Researcher (not Participant)

Use your FIU email if you have one active; otherwise yasiramalik@gmail.com. The FIU email helps with the "academic research" trust signal.

Verify the email link CloudResearch sends.

When asked for organization, enter Florida International University — DBA Program, Cohort 7.16.

✅ Done? Take a screenshot of the dashboard for your records. Stop here. Move to Step 2 when you have a free 10 minutes.

## Step 2 — Add funds (10 minutes) — *do this BEFORE you build the study so launch isn't blocked*

CloudResearch charges participant pay + platform fee. Budget for the soft-launch:

| Phase | Responses | Pay/response | Subtotal | Platform fee (~20–35% — confirm on the funding screen) | Load this much |

|---|---|---|---|---|---|

| Soft-launch | 15 | $6.00 | $90 | ~$22–32 | $120 |

| Full launch | 65 more | $6.00 | $390 | ~$95–137 | $520 |

| Total budget for the whole study | 80 | | $480 | | ~$640 |

In the researcher dashboard, find Billing / Add Funds / Wallet (whichever label CloudResearch shows you).

Start with $120 to clear the soft-launch. You can top up later.

Use a card you're comfortable expensing.

⚠️ If the actual fee on screen is different from the table above, trust the screen, not the table. Adjust your top-up.

## Step 3 — Create the project (10 minutes)

Dashboard → Create New Study / Create Project

Study title (what participants see):

Audit Professional Judgment Survey — Academic Research (FIU)

Internal name (only you see):

YMalik_Anchoring_Bias_v1_SoftLaunch

Survey type: External study (because we're routing to Qualtrics)

Survey link: paste your anonymous Qualtrics link (include the completion redirect or completion code per CloudResearch's instructions).

Estimated completion time: 15–20 minutes

Compensation: $6.00 USD

IRB info: paste protocol IRB-25-0462, PI/approval per IRB letter.

✅ Save as draft. Don't submit yet.

## Step 4 — Screening (the most important step) (15 minutes)

This is where you filter for audit professionals, not the general population. CloudResearch's Connect platform has pre-screened occupational and demographic filters — use them.

Required filters (turn ON):

Country: United States (matches IRB-approved population)

Language: English — Fluent

Employment status: Employed full-time OR Employed part-time

Industry / Occupation: Accounting / Auditing / Finance (use the closest match available)

Education: Bachelor's degree or higher

Custom screener questions (add 2–3 inside CloudResearch):

Q1. Are you currently, or have you been within the last 24 months, employed in an audit-related role (external audit, internal audit, or audit support)?

○ Yes  ○ No (screen-out)

Q2. Have you personally worked on at least one continuing audit engagement (multi-year engagement with the same client)?

○ Yes  ○ No (screen-out)

Q3. Confirm you are completing this survey on your own, without sharing it, and you have not seen it before.

○ Yes, I confirm  ○ No (screen-out)

Quality controls (already in the survey, but check the box on CloudResearch where available):

Block duplicate IPs

Block repeat participants

Enable bot/suspicious-activity detection

Enable hand-coded review of open-text response

## Step 5 — Soft-launch settings (5 minutes)

Sample size: 15 (soft-launch only)

Launch type: Soft-launch / pilot batch if CloudResearch offers it; otherwise just set N=15 and pause after.

Auto-approve: OFF for soft-launch — you review manually.

Estimated launch date: Wed Jun 24, 2026.

✅ Save. Don't submit yet.

## Step 6 — Pre-launch review (the night before, Tue Jun 23)

Run through this checklist before clicking Launch:

[ ] Qualtrics link opens, consent loads, and the survey starts on a real mobile device (your Pixel) AND a desktop browser.

[ ] Eligibility branching works — try one "ineligible" path and confirm screen-out.

[ ] Completion redirect URL from CloudResearch is pasted into Qualtrics' end-of-survey logic.

[ ] Compensation amount, IRB number, and study title match the IRB-approved language.

[ ] Funds in the CloudResearch wallet ≥ $120.

[ ] Both attention checks fire and the page-timing controls are on.

## Step 7 — Launch (2 minutes, Wed Jun 24)

Open the project draft → Submit for Review (CloudResearch reviews academic studies before activation — typically <24h, sometimes minutes).

Once approved, click Launch (or Activate).

Stay near the dashboard for the first hour. Watch the first 3–5 responses come in. If anything looks off (every response is 90 seconds, every response fails attention checks, etc.) — PAUSE THE STUDY immediately and message me.

## Step 8 — Monitor (Wed Jun 24 evening → Thu morning)

After 15 responses land:

Pause the study (it should auto-pause at N=15 since that's the limit).

Export the responses from Qualtrics + match against CloudResearch's participant log.

Check: attention-check pass rate, median completion time, screen-out rate.

Decision: clean → unpause for full launch (target n=80) OR pause + revise wording.

This decision goes in W07 (due Sun Jun 28) as the data-collection-progress update Dr. Rey asked for.

## If you get stuck on a step

Tell me which step number and what the screen says. Don't troubleshoot alone for more than 10 minutes — CloudResearch's UI changes faster than docs do, and a quick redirect is cheaper than an hour of friction.

## What this gets you

Wed Jun 24 evening: 10–15 valid responses in hand.

Sun Jun 28: W07 reports "data collection live; n=X collected, attention-check pass rate Y%, soft-launch quality decision: proceed/revise."

Jul 5 (W08): scaling toward 60–80.

Jul 12 (W09): collection closes; cleaning + descriptive analysis begins.

Jul 19: final manuscript with EFA results.

That's the lane. Now go run Step 1.