# Open Questions — Resolve These to Finish (Jul 23, 2026)

Deadlines: submit Friday · Sunday latest · Tuesday hard (else Incomplete).

## Chapter status at a glance

| Chapter | Status | What's blocking |

|---|---|---|

| Ch. 1 Introduction | 🔴 BLOCKED — needs Yasir | Current text lives in OneDrive (FIU-DBA 7.10/7 - Research Project), not accessible from this environment. Upload the Ch. 1 file to this chat, or copy it to Google Drive/Dropbox. Also: any specifics remembered from Dr. Rey's Ch. 1 feedback. |

| Ch. 2 Lit Review | ✅ Done | Nothing — stands per meeting. |

| Ch. 3 Model & Hypotheses | ✅ Done | Nothing — stands per meeting. |

| Ch. 4 Methodology | ✅ Done (v2, verified) | Yasir read-through in own voice. |

| Ch. 5 Data Analysis | ✅ Done (v2, verified) | Yasir read-through in own voice. |

| Ch. 6 Conclusions | ✅ Done (v2 + AI/risk enhancement, 10 verified sources) | Yasir read-through in own voice. |

| Appendix A | ✅ Done | Nothing. |

| Final assembly | ⏳ Waiting on Ch. 1 | Merge Ch. 1–6 + Appendix A → format → export Word/PDF → Canvas. |

## Open questions only Yasir can answer

Chapter 1 source file — upload it (or to Google Drive/Dropbox). Without it, Friday slips to Sunday.

Dr. Rey's Ch. 1 feedback — what did he actually say needed improving? Even fragments (problem statement? research questions? significance? alignment with final scope?).

Send the confirmation email (drafted, in correspondence/2026-07-23_Rey_meeting_confirmation.md + progress version in chat) — has it gone out yet?

Prolific decision — see Prolific_Recovery_Plan.md: pause the still-active study and recover ~$980, or leave it running? (Recommendation: pause today.)

UGS Mentoring-Plan Hold — any reply yet from ugs@fiu.edu or Ximena Lainez? Fall registration depends on it (classes Aug 24).

Simulated-data exercise — arrives from Dr. Rey after submission; tell me when it lands and we run it via the Jamovi runbook.

## Admin parking lot (not blocking Friday)

MyFIU: confirm hold cleared → register for Fall.

Prolific: enable MFA on the account (banner warning).

Dissertation: IRB scope amendment before any London/Canada recruiting.