# 📊 Progress Tracker — Final Sprint to Manuscript

Goal: Final manuscript submitted by Jul 18–19, 2026.

Status: ON TRACK — the two hardest blockers (survey + recruiting platform) are DONE.

## ✅ DONE (as of Jul 1)

[x] Research model, hypotheses, full paper (Ch. 1–3) — done earlier

[x] Instrument finalized (v2.1) + audit-practitioner peer review incorporated

[x] Survey built in Qualtrics — 73 items, 20 blocks, content-audited

[x] Anonymity + bot/duplicate protection configured

[x] Consent added + survey PUBLISHED LIVE

[x] Verified working end-to-end on mobile; question tags cleaned up

[x] CloudResearch researcher account created (40% edu discount)

[x] CloudResearch project draft built — Survey type, 15 × $6.00, US, $90 total

[x] Live link: https://fiu.qualtrics.com/jfe/form/SV_3lae5xJsPcRfIN0

## 🔜 IN PROGRESS / NEXT

[ ] Send pilot link to Richard + 2–4 audit contacts

[ ] Dr. Rey methodology meeting — Thu Jul 2, 11:00 AM

[ ] Finalize survey for paid launch:

[ ] Swap interim consent → exact IRB-approved letter

[ ] Wire screen-out branching (CONSENT/S1–S5 = No → End)

[ ] Paste CloudResearch completion redirect into Qualtrics end-of-survey

[ ] Re-add $6.00 line + (post-meeting) block randomization

[ ] Re-add US targeting + devices in CloudResearch

[ ] Fund CloudResearch (~$90) → LAUNCH soft-launch (15)

## 📅 Timeline

| When | Milestone | Status |

|---|---|---|

| Jul 1 | Survey LIVE | ✅ DONE |

| Jul 1 | CloudResearch project built (draft) | ✅ DONE |

| Jul 1–2 | Pilot link to Richard + friends | 🔜 |

| Jul 2, 11 AM | Dr. Rey methodology meeting | 📅 scheduled |

| Jul 2–3 | Finalize survey → fund → soft-launch (data begins) | ⬜ |

| Jul 3–8 | Scale to n = 60–80 | ⬜ |

| Jul 9–10 | Clean data | ⬜ |

| Jul 11–13 | EFA + mediation | ⬜ |

| Jul 14–17 | Write Results (Ch. 4) + Discussion (Ch. 5) | ⬜ |

| Jul 18–19 | Submit final manuscript | 🎯 |

Weekly updates: W08 (Sun Jul 5) "collection live, n = X" · W09 (Sun Jul 12) "collection closed; EFA underway."

## 🔑 Key references

Live survey: https://fiu.qualtrics.com/jfe/form/SV_3lae5xJsPcRfIN0

CloudResearch completion redirect (wire into Qualtrics): https://connect.cloudresearch.com/participant/project/96563A2A43/complete (code 96563A2A43)

Repo: https://github.com/AuditingAI/Profile/tree/claude/scholar-links-review-Plgk6/dba

Dr. Rey meeting agenda + email: correspondence/2026-06-30_Rey_meeting_July2_request.md

Full status: LIVE_Survey_Status.md

The hard part is behind you. From here it's execution on a clear, dated path.