## 1. Pre-Pilot Gate
Pre-Pilot Readiness Gate
All items must be GREEN before the informed pilot link is shared with any participant.
# | Gate Item | Owner | Evidence Required | Status | Date Cleared | Notes
1 | Qualtrics build matches IRB-approved instrument (IRB-25-0462); deltas filed as non-substantive change or amendment. | Yasir | Side-by-side check vs. IRB-approved PDF; advisor sign-off note. | Pending
2 | Consent block in Qualtrics presents the full informational letter and a forced-choice consent question. | Yasir | Screenshot of the consent page from a clean preview link. | Pending
3 | Eligibility screener filters non-eligible respondents into End-of-Survey before the construct items load. | Yasir | Qualtrics survey flow screenshot showing branching. | Pending
4 | Two attention checks embedded (per Appendix A.4 and A.8) and configured to mark failures, not auto-terminate. | Yasir | Qualtrics logic screenshot; results variable defined. | Pending
5 | Reverse-coded items render correctly and the data dictionary captures direction. | Yasir | Item-by-item export from Qualtrics; reverse-coding key. | Pending
6 | Progress bar enabled; estimated completion time displayed at start. | Yasir | Preview screenshot from start of survey. | Pending
7 | Mobile-responsive layout tested on phone and tablet. | Yasir | Two screenshots: phone preview, tablet preview. | Pending
8 | No personally identifying or client-identifying fields collected (consistent with IRB scope). | Yasir | Field-by-field audit against IRB approval. | Pending
9 | Advisor face-validity sign-off on full Qualtrics build. | Dr. Rey | Email or meeting note from Dr. Rey confirming sign-off. | Pending
10 | Pilot Participant Log (Pilot_Feedback xlsx, Tab 1) opened and ready for entries. | Yasir | File saved at 03_Recruitment_and_Pilot/ with first row populated. | Pending

## 2. Pilot Close-Out Gate
Pilot Close-Out Gate
All items must be GREEN before the recruiting platform listing goes live.
# | Gate Item | Threshold / Decision Rule | Status | Date Cleared | Notes
1 | Pilot sample size achieved. | n = 6-10 eligible auditors completed both the survey and the feedback form. | Pending
2 | Median completion time within target. | 15-20 minutes; flag if outside band. | Pending
3 | No respondent reported items that were unclear, leading, or domain-inappropriate. | PF1-PF4 mean >= 4.0 on the 1-5 scale across pilot respondents. | Pending
4 | No structural item changes required. | Severity column on Revision Log shows no entries flagged High and no entries flagged 'Advisor/IRB Review Needed = Yes'. | Pending
5 | Attention-check failure rate within tolerance. | <= 10% of pilot respondents failed either attention check. | Pending
6 | Pilot Decision Summary tab fully populated and all criteria status = Met. | All criteria on the Pilot Decision Summary tab = Met. | Pending
7 | Advisor sign-off to proceed to recruiting platform. | Dr. Rey confirms via email or meeting note. | Pending
8 | Any IRB amendment triggered by pilot revisions has been filed and acknowledged. | Topaz confirmation number on file; if no amendment required, note that here. | Pending

## 3. CloudResearch Gate
CloudResearch Launch Gate (Primary Recruiting Route)
Gate Items 1-8 must be GREEN before the CloudResearch study listing is set to Live. Gate Items 9-12 govern the soft launch.
# | Gate Item | Owner | Evidence Required | Status | Date Cleared | Notes
1 | Study listing copy reviewed against the CloudResearch Launch Draft (READY 2026-06-01). | Yasir | Diff vs. approved draft. | Pending
2 | Compensation amount confirmed with advisor and within CloudResearch fair-pay band. | Yasir + Dr. Rey | Advisor confirmation; cross-check vs. CR fair-pay calculator. | Pending
3 | Quality filters configured: approval rating, prior-participation exclusion, geo, audit-profession screener. | Yasir | Screenshot of CR filter panel. | Pending
4 | Do-not-add boundaries verbalized in the listing (no AI/LLM constructs, no fabricated identity). | Yasir | Listing copy review. | Pending
5 | Time estimate in the listing matches pilot median completion time. | Yasir | Pilot data + listing copy. | Pending
6 | Survey link routes from CR to Qualtrics with the CR participant ID embedded. | Yasir | Test link round-trip: CR -> Qualtrics -> CR completion code. | Pending
7 | Completion code returned to CR for crediting; failure path returns a distinguishable code. | Yasir | Screenshot of CR validation panel; two test runs. | Pending
8 | Data export path validated: SPSS / CSV / SAV download from Qualtrics works for at least one test response. | Yasir | Downloaded test file saved locally. | Pending
9 | Soft launch n = 10-15 only; pause for 24 hours to inspect data quality. | Yasir | Date/time of soft-launch open and close. | Pending
10 | Soft-launch quality review: attention-check pass rate, straight-lining check, completion-time outliers. | Yasir | One-page review note saved to correspondence/. | Pending
11 | Decision to proceed to full launch (n = 60-80 target) or pause for fixes. | Yasir + Dr. Rey | Advisor acknowledgement. | Pending
12 | Full-launch ongoing data quality monitoring cadence agreed (every 20 responses). | Yasir | Cadence noted in this sheet. | Pending

## 4. MTurk Backup Gate
MTurk Backup Gate (Conditional — only if CloudResearch yield insufficient)
Do not open MTurk concurrently with CloudResearch. Open only if CR yields below target after the full-launch window.
# | Gate Item | Owner | Evidence Required | Status | Date Cleared | Notes
1 | CloudResearch yield confirmed below target after defined full-launch window. | Yasir | Yield report from CR; advisor confirmation that backup is needed. | Pending
2 | MTurk HIT copy reviewed against the MTurk Backup Launch Draft (READY 2026-06-01). | Yasir | Diff vs. approved draft. | Pending
3 | Qualifications set: HIT approval rate, master qualification, audit screener. | Yasir | Screenshot of HIT qualifications panel. | Pending
4 | Duplicate-participant exclusion: CR completion IDs added to MTurk exclusion list. | Yasir | Exclusion list confirmed. | Pending
5 | Per-assignment reward consistent with CR rate. | Yasir | Cross-check. | Pending
6 | Same survey-link round trip and completion-code validation as in the CR gate. | Yasir | Two test runs. | Pending
7 | Soft launch n = 5-10 on MTurk first. | Yasir | Date/time of soft-launch open and close. | Pending
8 | Decision to scale or pause MTurk arm; advisor sign-off. | Yasir + Dr. Rey | Advisor acknowledgement. | Pending

## 5. Stop Conditions
Stop / Pause Conditions During Live Recruitment
If any condition triggers, pause data collection on the affected route within 24 hours and document the pause in the Revision Log.
# | Condition | Detection Method | Pause Action | Owner | Triggered? (Y/N) | Notes
1 | Attention-check failure rate exceeds 15% across the last 20 responses. | Rolling check from Qualtrics export. | Pause CR / MTurk; review item wording. | Yasir | N
2 | Straight-lining detected in > 10% of responses. | Variance < 0.5 across construct items. | Pause; consider adding a second behavioral check. | Yasir | N
3 | Median completion time drops below 8 minutes or exceeds 35 minutes. | Qualtrics duration export. | Pause; review the listing time estimate. | Yasir | N
4 | Eligibility-screener pass rate falls below 30%. | Eligible / Total in Qualtrics. | Adjust screener wording; refile if material. | Yasir | N
5 | Any respondent reports a privacy or sensitive-data concern. | Feedback channel monitored daily. | Pause immediately; report to FIU IRB if applicable. | Yasir | N
6 | Platform-level concern flagged by CR or MTurk worker community. | Daily check of platform-specific worker forums. | Pause the affected route; consult advisor. | Yasir | N