# Recruitment Sprint — Handoff & Live Tracker

Owner: Yasir A. Malik · Helping: Sarmed

Goal: n = 100 valid US audit-professional survey responses by Jul 11.

Why the urgency: final manuscript due Jul 18–19; data must be in by ~Jul 11 to leave time for EFA + reliabilities + write-up.

Live survey (share this): https://fiu.qualtrics.com/jfe/form/SV_3lae5xJsPcRfIN0

Context: CloudResearch's self-service panel can't reach auditors. Dr. Rey recommended Prolific — that is now our PRIMARY route (prescreens by occupation/industry, fast, cheaper than managed research). CloudResearch Managed Research is the backup. The survey is LIVE via the direct link now.

## 🔴 Live Tracker

| # | Task | Owner | Due | Status |

|---|---|---|---|---|

| 1 | Set up Prolific study (account → build → prescreen US audit/finance → check eligible count → soft-launch 15) — see Prolific_Setup_Guide.md | Sarmed + Yasir | Jul 2 | ☐ |

| 2 | Report Prolific eligible-participant count (tells us if supply is there) | Sarmed | Jul 2 | ☐ |

| 3 | Finalize Qualtrics for launch (consent letter, Prolific completion redirect + PROLIFIC_PID, force-response) | Sarmed + Yasir | Jul 2 | ☐ |

| 4 | BACKUP: get CloudResearch Managed Research quote (only if Prolific supply thin) | Sarmed | Jul 3 | ☐ |

| 5 | Free outreach — LinkedIn + IIA/AICPA chapters + FIU alumni | Sarmed | Jul 2 | ☐ |

| 6 | Provide IRB consent letter + approve spend | Yasir only | Jul 2 | ☐ |

| 7 | Fund Prolific + scale to 100 | Yasir only | Jul 3 | ☐ |

| 8 | Daily response tracking toward n=100 (flag attention-check fails/speeders) | Sarmed | Daily | ☐ |

| 9 | Hit n = 100 valid | Both | Jul 9–10 | ☐ |

Reporting cadence: Sarmed sends a 1-line status every evening (e.g., "Quotes: 2/3 back. Responses: 12. LinkedIn posted."). Update this table's Status column each time.

## 📋 Study spec (paste into any panel quote request)

N size: 100 valid completes (ask each panel how many to oversample for screen-outs)

Audience: U.S.-based audit professionals — current or within last 24 months in external audit, internal audit, or audit support; experience on ≥1 continuing (multi-year) engagement; bachelor's+; English-fluent

Survey length: ~15–20 min (anonymous, single session, ~73 items)

Quotas: none required; a mix of external/internal auditors preferred if feasible

Other: academic dissertation research (FIU DBA), IRB-25-0462; anonymous, on FIU Qualtrics; no download/video; not longitudinal/dyadic; has screeners + attention checks

Budget: request a quote first (specialized auditor panels can run $20–$50+/complete)

## ❓ Ask every panel the same 3 questions

Total cost for 100 verified US auditor completes?

Realistic timeline to deliver?

How do you verify the audit occupation (not just self-report)?

## 🔧 Qualtrics finalize checklist (task 4)

Full steps in Qualtrics_Codebook_and_Setup.md. Summary:

[ ] Survey Flow: CONSENT/S1–S5 = "No" → End of Survey (screen-outs)

[ ] Block 00: paste exact IRB-approved consent letter (Yasir provides)

[ ] Force-response ON for construct + screener questions

[ ] Add chosen panel's completion redirect to end-of-survey

[ ] Preview both eligible + screen-out paths on mobile + desktop

## 📣 Free outreach (task 5)

LinkedIn: post in audit/accounting groups + personal networks with the live link

Associations: email IIA & AICPA local chapters

FIU alumni in audit/accounting

Keep a list of who shared it (for follow-up)

## Boundaries (do not cross)

Anonymous only — no employer/client/engagement names, no PII

Wording/flow of the survey stays fixed (it's peer-reviewed + IRB-approved); Sarmed configures logistics, not content

Any spend approved by Yasir before it happens