Informed Pilot Protocol

6-10 auditor pilot for face validity, clarity, flow, timing, and technical readiness

| Status | READY for informed pilot after Qualtrics preview testing |
| --- | --- |
| Date | 2026-06-01 |
| Model Scope | TA, RA, AT, SAP, FR, IR, RPG, PMI -> AJQ/APR -> RAB; no AI/LLM constructs in the current survey |

# Purpose

The pilot is an informed pilot, not a statistical pilot. Its purpose is to confirm face validity, item clarity, audit-language fit, completion time, screen flow, and technical functioning before paid recruiting begins.

# Pilot Participants

Target 6 to 10 auditors who meet the same survey eligibility standards.

Participants should be age 18 or older, current/recent auditors, have at least 2 years of audit experience, and have long-term engagement or prior-period evidence exposure.

Pilot participants should not be asked to disclose employer names, client names, confidential workpapers, account-level data, or sensitive personal data.

# Pilot Procedure

Build the Qualtrics survey using the launch packet and export map.

Run all preview tests before distributing a pilot link.

Send the pilot link with a short note explaining that feedback is requested on clarity, flow, and completion time.

Ask pilot participants to complete the survey first and then complete the pilot feedback form.

Record completion time, confusing wording, technical issues, and any scope-affecting concern in the pilot revision log.

Revise wording/flow only when the change stays within approved constructs and IRB scope.

# Decision Rules

| Area | Trigger | Action |
| --- | --- | --- |
| Clarity | Average clarity below 4/5 or repeated confusion | Revise wording only; preserve construct meaning |
| Construct fit | Average construct-fit rating below 4/5 | Review wording and flag for advisor if construct meaning may shift |
| Audit-language fit | Pilot feedback says wording is not natural for auditors | Revise audit phrasing without adding new constructs |
| Response burden | Completion time exceeds 20 minutes or fatigue comments repeat | Review redundancy; avoid removing items unless advisor approves |
| IRB scope | Feedback suggests adding AI, new populations, sensitive data, or new substantive domains | Do not revise directly; flag for advisor/IRB review before launch |

# Launch Readiness Evidence

Qualtrics preview path passed for eligible and screen-out respondents.

Survey completion time is approximately 15 to 20 minutes.

No sensitive personal, financial, clinical, employer, client, or account-level data requested.

IP retention/anonymity settings match proposal and IRB language.

Export test confirms variable names and reverse-code flags match the map.

Pilot revision log documents what changed, why, and whether advisor review was needed.