# WEEKLY PROJECT UPDATE — Week 5 (Catch-Up)

DBA Research Project · Qualifying Examination

## Honest header

Two weekly updates were missed (W02 and W03). This update covers the W02–W04 reporting period and re-baselines Week 5 commitments. The READY packet I prepared on June 1 in response to Dr. Rey's instructions has been on the project branch the whole time; the gap was in execution, not in deliverables.

## Current Stage(s)

Stage 1 — Instrument (PRIMARY this week — Qualtrics build is the gating activity)

Stage 2 — Informed Pilot (READY packet filed, awaiting Stage 1 closure)

Stage 3 — Recruiting platforms (CloudResearch + MTurk drafts READY)

Stage 0 — IRB: Protocol IRB-25-0462 active; Topaz PI-change amendment outstanding

## What changed during W02–W04

June 1: Built and committed the full READY packet to the project repo in response to Dr. Rey's feedback: revised paper (v4.1 → v4.2), informed-pilot protocol, feedback/revision workbook, CloudResearch and MTurk launch drafts, recruiting launch checklist, interactive dashboard, build-and-launch guide.

June 1–14: Did not advance the Qualtrics build, the face-validity meeting, or the pilot launch. No new IRB activity. No advisor communication.

Repo state today: clean, pushed, branch claude/scholar-links-review-Plgk6. Every artifact named below is at a verifiable commit.

## Re-baselined plan for Week 5 (June 15–21)

| Date | Deliverable | Status gate |
| --- | --- | --- |
| Mon June 15 | Open dashboard; reconcile first 3 constructs (TA, RA, AT) against IRB-approved instrument | Begin reconciliation log |
| Tue June 16 | Finish reconciliation across all 11 constructs; commit reconciled item list | Reconciliation log filed |
| Wed June 17 | Build consent + screeners + first 5 construct blocks in Qualtrics | Mid-build commit |
| Thu June 18 | Finish remaining 6 construct blocks + demographics + randomizer + anonymity settings | Preview test passes |
| Fri June 19 | Brief Zoom with Dr. Rey: face-validity sign-off, LinkedIn copy sign-off, CloudResearch compensation amount | Three sign-offs in hand |
| Sat June 20 | Send pilot invitations to 6–10 LinkedIn audit contacts | P01–P10 logged |
| Sun June 21 | Pilot collection underway (target ≥6 by Wed June 24) | Pilot active |

## Risks and how I'm handling them

Risk: another execution gap. Mitigation: daily commit cadence on the project branch; missing a day triggers a one-line note to Dr. Rey, no excuses.

Risk: IRB-scope drift during pilot. Mitigation: the READY decision rules already specify that any scope-affecting feedback halts revision and escalates to advisor / Topaz before any change.

Risk: CloudResearch yield insufficient. Mitigation: MTurk backup draft is READY; LinkedIn parallel channel provides 30–40 of the n=60–80 target.

Risk: July 19 manuscript milestone. Mitigation: re-baselined plan preserves a 3-week data collection window (June 29 – July 12) and a 1-week analysis-and-write window before the milestone.

## What I am asking Dr. Rey for

A 20-minute Zoom this week (any time on or before Friday June 19)

Face-validity sign-off on the Qualtrics build during that Zoom

Sign-off on the LinkedIn outreach copy (3 templates)

Confirmation of the CloudResearch compensation amount

## Boundaries I am holding to

No AI/LLM items in this survey (reserved for future research)

No employer / client / account-level / sensitive personal data

Wording-and-flow-only revisions during the pilot; any scope-affecting change halts for advisor + IRB

## Schedule snapshot

Now: closing Week 4 / opening Week 5 of 9

Pilot window: June 20 – June 27

CloudResearch data window: June 29 – July 12

Analysis + Chapter 5 write: July 13 – July 18

Stage 4a manuscript milestone: July 19, 2026

Student: Yasir A. Malik (PID 1687105) | Cohort 7.16

Advisor: Prof. Dr. Juan Rey, FIU DBA Program

Submitted: Sunday, June 14, 2026