# Daily Sprint — Jul 9 → Jul 19

Standing facts: 20 valid responses · free-channel recruitment (funding constraint) · analysis scope = EFA + reliabilities only (Scope Amendment v2.1) · manuscript ships Jul 18–19 regardless of final n.

Daily rhythm: one must-do per day + evening response count logged. Everything else is bonus.

| Day | Must-do | Also (if energy allows) | Evening check-in |

|---|---|---|---|

| Wed Jul 9 | Send Dr. Rey the status email (20 responses + 3 questions) | LinkedIn repost + ask 5 contacts to reshare; IIA/AICPA chapter emails (Outreach_Kit template #6) | Count + "email sent" |

| Thu Jul 10 | Cohort + FIU alumni email blast (template #5) | Sarmed check-in; [if any budget: fund partial Prolific batch] | Count |

| Fri Jul 11 | Log honest count vs the original n=100 date; keep collecting | Install SPSS (FIU portal); Qualtrics export dry-run | Count + SPSS working? |

| Sat Jul 12 | Weekly Update (W09) due Sunday — draft + submit to Canvas (stage format; reuse W08 pattern with current numbers) | Apply any Dr. Rey answers from the email | Count + W09 submitted |

| Sun Jul 13 | LAST collection day. Evening: freeze survey + final Qualtrics export (numeric + choice text) into raw/ | Final reshare push in the morning | Final n locked |

| Mon Jul 14 | Clean: exclusion log (attention fails, speeders, screeners), reverse-code the 11 (R) items, outlier screen, descriptives + normality | — | Analytic n + exclusion table done |

| Tue Jul 15 | EFA + reliabilities per Playbook: KMO/Bartlett/anti-image/determinant → PAF + scree → both rotations (report Oblimin) → item rule → Cronbach's α + item-total | Draft the Data Analysis section same evening (fill-in template in Playbook Step 5) | Pattern matrix + α table done |

| Wed Jul 16 | Write Results narrative (exemplar order: pilot → build → collection → validation → outliers → demographics → normality → EFA → reliability) + Conclusions with the small-n limitation stated plainly | — | Results drafted |

| Thu Jul 17 | Assemble full manuscript on the exemplar skeleton (I–VI + lettered appendices) · run the rubric self-score | Fix everything the self-score flags | Full draft exists |

| Fri Jul 18 | Your full read end-to-end + fixes · Turnitin if available | Final consistency sweep (names, numbering, APA 7) | Ready to submit |

| Sat Jul 19 | SUBMIT to Canvas (final naming, 07_Final_Submission trail) · confirm to Dr. Rey | — | 🎯 DONE |

## Small-n contingency (pre-decided so Jul 14 needs no thinking)

n ≥ 50: run the EFA; report KMO/Bartlett exactly as they come out; note sample size in limitations.

n 30–49: run the EFA as exploratory evidence; lead the Data Analysis with adequacy diagnostics; frame findings as preliminary validation; heavier limitations section (already drafted in Methodological_Limitations_and_Remedies).

n < 30: default to descriptives + reliability (α) + item-level analysis, and present the EFA plan as specified-but-underpowered — unless Dr. Rey's answer to Question 2 says otherwise. His answer governs.

## The three questions in play (from the Jul 9 email)

Cutoff date — is Jul 13 freeze acceptable?

Minimum n floor for running the EFA at all?

Any FIU/DBA no-cost distribution channel this week?

Whichever answers arrive, the dates above do not move; only the analysis branch (contingency table) adjusts.