# Timeline & Milestones — Final Sprint

Context: Dr. Rey (Jun 29): ~2 weeks to the final manuscript; begin collecting data immediately. Separately (Jun 29 class email): no pre-submission review of the manuscript or any section — this is the qualifying exam. Self-assess against the Canvas rubric; use prior-course analysis tutorials.

Operating rule for the next two weeks: the advisor is a resource for specific methodological questions asked in advance (the July 2 meeting), not a reviewer of drafts. Plan and quality-check independently against the rubric.

## Milestones (gate = must be true to move on)

| # | Milestone | Target date | Gate / definition of done |

|---|---|---|---|

| M1 | Survey live in Qualtrics | Tue Jun 30 (tonight) | Imported, consent + screen-outs wired, preview-tested both paths, anonymous link published |

| M2 | CloudResearch ready | Tue Jun 30 | Account funded ($120), project drafted with screeners + $6.00 + IRB-25-0462, link pasted, submitted for review |

| M3 | 1-day micro-pilot | Wed Jul 1 AM | 3–4 contacts confirm it works end-to-end; wording-only fixes applied |

| M4 | Data collection begins | Wed Jul 1 | CloudResearch soft-launch (15) live |

| M5 | Soft-launch quality gate | Thu Jul 2 | Attention-check pass rate, median time, screen-out rate reviewed → go/no-go to full launch |

| M6 | Methodology questions to Dr. Rey | ✅ Jun 30 | Answered by email — n=100, PAF + Direct Oblimin, EFA+reliabilities only, item rule. Meeting declined per his recommendation to focus on collection. |

| M7 | Full sample collected | Wed Jul 8 | n = 100 valid responses; collection closed; data exported |

| M8 | Data cleaned | Fri Jul 10 | Reverse-coded; attention-fails/speeders/duplicates removed; analytic n documented; descriptives done |

| M9 | EFA + reliabilities complete (FINAL ANALYSIS) | Mon Jul 14 | KMO + Bartlett; PAF; parallel analysis; Direct Oblimin rotation; pattern matrix; item removal (<.30; .30–.40 case-by-case); Cronbach's α per factor |

| ~~M10~~ | ~~Mediation~~ | — | Out of scope per advisor directive (no mediation/hypothesis testing this term) |

| M11 | Results + Discussion written | Thu Jul 17 | Ch. 4 (Results) + Ch. 5 (Discussion) drafted and integrated |

| M12 | Final manuscript submitted | Sat–Sun Jul 18–19 | Rubric self-check passed; citations re-verified; formatted; uploaded to Canvas |

Weekly updates: W08 (Sun Jul 5) — "collection live, n = X." W09 (Sun Jul 12) — "collection closed; cleaning + EFA underway."

## Tonight (Jun 30) — the only thing that matters: hit M1

fiu.qualtrics.com → Create → Tools → Import survey from TXT → Qualtrics_Survey_Import.txt (peer-reviewed v2.1).

Paste IRB consent into Block 00.

Wire screen-out branching (codebook Step 2).

Survey options: anonymous ON, IP OFF, force-response ON, progress bar ON, bot/duplicate protection ON.

Preview both paths (eligible + screen-out) on phone + desktop.

Publish → copy the anonymous link.

Paste link into the CloudResearch draft → submit for review (M2).

Send the link to 3–4 contacts for the 1-day micro-pilot (M3).

Send the July 2 meeting email to Dr. Rey.

If you only do one thing tonight, do M1. Everything downstream depends on the link existing.

## Rubric alignment (since there is no external review)

Pull the Canvas rubric and self-score the manuscript against it before submitting. Typical DBA qualifying-exam weight sits on: problem/significance, literature grounding, model & hypotheses, methodology rigor, results/analysis correctness, interpretation, and writing. The first three are already strong in the paper; the next two are what the next two weeks produce. Build the Results section to answer the rubric's analysis criteria point-for-point.

## Risk plan

Slow recruitment (n < 30 by Jul 5): launch the MTurk backup in parallel + post LinkedIn outreach.

A construct under-performs in EFA: report it honestly; EFA is a validation study, so a factor that splits or collapses is a finding, not a failure.

Time compression on writing: Results + Discussion are the only new chapters; Ch. 1–3 are done. Protect Jul 14–17 for writing — do not let analysis bleed into it.