# Student Project Update — Yasir A. Malik

PID 1687105 | Cohort 7.16 | GEB7913

Reporting period: June 29 – July 5, 2026 (Week 8)

Current stage: Stage 3a — Recruitment and Data Collection (data collection is now underway)

Stage 1a — Recruitment and Solicitation materials. Outreach is active. The survey was distributed through multiple free channels — LinkedIn (post to audit/accounting networks with a reshare request), WhatsApp (personal and group), and direct outreach to audit-professional contacts. Cohort and professional-association (IIA/AICPA chapter) outreach is queued. A shared outreach kit (LinkedIn, WhatsApp, email, and association templates) was created to keep messaging consistent.

Stage 1b — Executing the Informed Pilot. Underway. The live instrument was distributed to audit-experienced contacts for an informal cross-device check of the consent flow, item comprehension, and timing; feedback continues to be logged and applied as wording-only adjustments.

Stage 1c — Documenting the informed pilot in the manuscript. No update.

Stage 2a — Design and implementation in Qualtrics. Complete. The instrument (v2.1, 73 respondent-facing items) is built and published live in FIU Qualtrics, verified end-to-end on mobile and desktop. It reflects two rounds of peer review (an audit-practitioner wording review and a methodological review), with anonymity, bot/duplicate protection, and embedded attention checks enabled.

Stage 2b — Integration into recruiting platform. In progress. CloudResearch Connect (self-service) was found not feasible for this audience — verified audit professionals are a specialized population the self-service panel cannot reliably reach. The study is therefore transitioning to CloudResearch Managed Research (dedicated recruitment of the auditor sample), with a quote in progress; competing panel quotes are being gathered in parallel. I will be funding the paid panel to complete the sample.

Stage 3a — Recruitment and Data Collection. Data collection has begun. 12 valid responses have been collected to date through organic outreach. Collection is scaling toward the target of n = 100 valid via the paid panel plus continued outreach. I expect meaningful progress on the response count by the next update.

Stage 3b — Data cleaning and scrubbing. No update.

Stage 3c — Descriptive Analysis. No update.

Stage 3d — Factor Analysis and revisions based on loadings. No update.

Stage 4a — Finalize the manuscript. The analysis scope is confirmed per your guidance: the Data Analysis section will cover EFA + reliabilities (Principal Axis Factoring with Direct Oblimin rotation; suppress loadings < .30; remove < .30 and decide .30–.40 case-by-case; Cronbach's α per factor) on the n = 100 sample. A Methodological Limitations & Remedies section was drafted to address self-report, social desirability, common method variance (Podsakoff et al., 2003), and discriminant validity (Fornell & Larcker, 1981). No changes to the model or hypotheses (retained as the proposed framework / future research).

Plan for the coming week. Fund and launch the managed panel to scale responses; continue cohort and association outreach; monitor response quality (attention checks, timing) daily; target n = 100 valid, then proceed to data cleaning, reliabilities, and EFA per the guided procedure. SPSS is being installed in preparation for analysis.

Repository. All artifacts live on the project branch claude/scholar-links-review-Plgk6 in the dba/ folder.

Boundaries held. Anonymous only; no employer/client/engagement-level or sensitive personal data. Survey content is peer-reviewed and IRB-approved (IRB-25-0462); wording/flow-only revisions during collection; any scope-affecting change escalates to advisor + IRB.