WEEKLY PROJECT UPDATE — Week 1

DBA Research Project  •  Qualifying Examination

Revised May 27, 2026 — clarifies re-baselined July 19 manuscript deadline and flags LinkedIn outreach copy pending advisor sign-off.

Current Stage(s)

Stage 1 — Informed Pilot (PRIMARY)

Stage 2 — Qualtrics & Survey Instrument (PARALLEL — leveraging IRB-approved instrument)

Note: Stage 0 (IRB) is complete — Protocol IRB-25-0462 was approved 09/02/2025 and is effective through 09/02/2030.

Stage 1a — Recruitment & Solicitation Materials

Drafted three-channel recruitment package: (i) MTurk HIT advertisement with auditor-qualification filters; (ii) LinkedIn outreach copy targeted to internal/external audit professionals with 2+ years experience; (iii) IIA-chapter referral note.

Informational Letter aligned to FIU exempt-research template and the IRB-approved 30-minute participation window.

Selection-criteria filters finalized: minimum 2 years audit experience; current internal or external audit role; exposure to long-term client engagements.

Stage 1b — Executing the Informed Pilot

Pilot panel identified: 6 auditors confirmed (2 Big-4 external, 2 internal-audit managers, 2 federal regulator-side reviewers); 4 additional invitations outstanding.

Pilot scheduled asynchronously (Qualtrics) with synchronous 15-minute debrief calls scheduled the following week to capture comprehension issues and timing data.

Stage 2a — Qualtrics Design & Implementation

Eleven-construct survey instrument (TA, RA, AT, SAP, FR, IR, RPG, PMI, AJQ, APR, RAB) deployed into FIU Qualtrics; validity-checking mechanisms in place: 2 reverse-coded items per construct, 3 embedded attention checks, page timers on all Likert pages, force-response on demographics.

Survey flow tested end-to-end on desktop and mobile; completion-time estimate from internal walkthrough = 18 minutes (within IRB-approved 30-minute ceiling).

Stage 2b — MTurk Integration

MTurk HIT scaffolded with Qualtrics survey link; auditor-qualification screener added; payment amount drafted per Florida-compliant compensation rules (no lottery, fixed payment).

Integration not yet live — gating on completion of Stage 1c (pilot revisions) before publishing the HIT.

Stage Completion Snapshot

Stage 0 (IRB approval): 100% complete

Stage 1a (Recruitment materials): 100% complete (LinkedIn copy pending advisor sign-off)

Stage 1b (Pilot execution): 0% — scheduled Week 2

Stage 2a (Qualtrics deployment): 95% — pilot revisions pending

Stage 2b (MTurk integration): 60% — gated on Stage 1c

Blockers / Risks Surfaced This Week

IRB Protocol IRB-25-0462 currently lists prior advisor as PI; amendment to reflect Prof. Rey as faculty advisor will be filed in Topaz this week (low-risk administrative amendment).

Stage 4a manuscript deadline tightened from prior planning (Aug 9) to July 19 per program guidance. Internal Semester Plan re-baselined; manuscript drafting accelerated into Weeks 6–8.

Next Week Priorities (Week 2 — May 25 – May 31)

Stage 1b: Execute pilot with 6 confirmed auditors; capture timing and comprehension data.

Stage 1c: Document pilot findings; identify Qualtrics revisions; classify as minor (no IRB amendment) vs. material (Topaz amendment).

Stage 2a: Apply pilot-driven revisions to the live Qualtrics instrument.

Submit IRB PI-change amendment in Topaz.

Obtain Prof. Rey sign-off on LinkedIn outreach copy before sending.

Student: Yasir A. Malik (PID 1687105)  |  Cohort 7.16

Advisor: Prof. Dr. Juan Rey, FIU DBA Program

Originally submitted: Sunday, May 24, 2026  |  Revised: May 27, 2026

Reporting Period: May 18 – May 24, 2026 (Project Week 1 of 9)