# Sprint to Manuscript — Data Collection Starts TODAY

Trigger: Dr. Rey (Jun 29): "Only 2 weeks remaining… begin collecting data immediately."

Principle: Everything that is not data collection waits. The instrument is finalized and peer-reviewed; the Qualtrics import file is ready. There is no more prep to do — only execution.

The one number that matters: get the survey live and collecting within 24 hours. Every day of collection saved is a day returned to cleaning, EFA, and writing.

## The compressed runway (Jun 30 → Jul 19)

| Date | Phase | Goal |

|---|---|---|

| Tue Jun 30 (TODAY) | Go live | Build + publish Qualtrics; send to 3–4 pilot contacts; set up CloudResearch |

| Wed Jul 1 | Soft-launch | CloudResearch soft-launch (15) — collection officially begins |

| Thu Jul 2 | Quality gate | Review first 15: attention checks, timing, screen-outs → go/no-go |

| Fri Jul 3 – Tue Jul 7 | Scale | Full launch toward n = 100 valid; monitor daily |

| Wed Jul 8 | Close | Stop collection; export data |

| Thu Jul 9 – Fri Jul 10 | Clean | Reverse-code, drop attention-check fails / speeders / duplicates; finalize analytic sample; descriptives |

| Sat Jul 11 – Mon Jul 14 | Analyze | EFA (KMO, Bartlett, parallel analysis, PAF + Direct Oblimin, loadings) + reliability (Cronbach's α). No mediation — out of scope per advisor. |

| Tue Jul 14 – Thu Jul 17 | Write | Results (Ch. 4) + Discussion (Ch. 5); integrate into manuscript |

| Fri Jul 18 | Polish | Proofread, citations re-verified, formatting |

| Sat–Sun Jul 18–19 | Submit | Final manuscript to Canvas |

Weekly updates continue: W08 (Sun Jul 5) reports "collection live, n = X"; W09 (Sun Jul 12) reports "collection closed, cleaning + EFA underway."

## TODAY — Tuesday June 30 (do these in order)

### ▢ 1. Build Qualtrics from the import file (45–60 min)

fiu.qualtrics.com → Create project → Tools → Import survey from TXT → upload Qualtrics_Survey_Import.txt (already v2.1, peer-reviewed wording).

Paste the IRB-approved consent letter into Block 00 (replace placeholder).

Wire screen-out branching in Survey Flow (codebook Step 2).

Survey options: anonymous ON, IP off, force-response ON, progress bar ON, bot/duplicate protection ON.

### ▢ 2. Preview-test both paths (15 min)

One pass as an eligible respondent (full flow + redirect).

One pass as an ineligible respondent (screen-out fires).

Test on your phone and a desktop.

### ▢ 3. Publish + grab the anonymous link (5 min)

Distributions → Anonymous Link → copy. This is the link everything else uses.

### ▢ 4. Send a 1-day micro-pilot (10 min)

Send the link to 3–4 audit contacts (Richard + others) with: "This is live now — if you can run through it today and flag anything broken, that's all I need. Going to full launch tomorrow."

This is the informed pilot, compressed to one day so it doesn't delay collection.

### ▢ 5. Set up CloudResearch (30 min)

If not already: create account, load funds ($120 for soft-launch).

Draft the project from CloudResearch_Setup_Guide.docx (study listing, screeners, $6.00, IRB-25-0462). Paste the Qualtrics anonymous link. Save as draft — submit for review tonight so it's approved by morning.

### ▢ 6. Send the meeting email to Dr. Rey (5 min)

Use correspondence/2026-06-30_Rey_meeting_availability_reply.md — fill three time slots, send today.

## Wednesday July 1 — Soft-launch

Apply any wording-only fixes from the micro-pilot (nothing substantive).

CloudResearch: submit/launch soft-launch batch of 15.

Watch the first hour. Pause if every response is <90s or fails attention checks.

Data collection has officially begun — this is the milestone for the W08 update.

## Thursday July 2 — Quality gate (the only decision point)

Review the 15:

Attention-check pass rate, median completion time, screen-out rate, open-text quality.

Clean → unpause to full launch (n = 80).

Problems → one round of wording-only fixes, then proceed.

## Friday Jul 3 – Tuesday Jul 7 — Scale

Top up CloudResearch to ~$640 total; raise target to 80.

Monitor once daily. No need to babysit.

Goal: n = 100 valid by Jul 8.

## What happens if collection is slow (risk plan)

By Jul 5, if n < 30: add the MTurk backup launch (draft already in 03_Recruitment_and_Pilot/) in parallel, and post the LinkedIn outreach to audit contacts.

EFA floor: EFA needs a workable subject-to-item ratio. With 55 construct items, aim for n ≥ 60; if collection stalls near 40–50, proceed with the analysis and report the sample limitation transparently — a complete manuscript on a smaller clean sample beats an incomplete one.

## The analysis is already specified (no decisions left for Jul 11)

When data lands, the plan is fixed:

Screen + clean: reverse-code position-4 items (6 − x); drop attention-check failures and implausibly fast responses; document the analytic n.

Factorability: KMO (≥ .70 target) + Bartlett's test of sphericity.

Extract: principal-axis factoring; decide # factors via parallel analysis + scree + eigenvalues.

Rotate: Direct Oblimin (oblique); inspect the pattern matrix; remove loadings < .30, and decide .30–.40 case-by-case (keep an item if removing it worsens the pattern matrix).

Reliability: Cronbach's α per retained factor (≥ .70).

Report: write the Data Analysis section (EFA factor structure + reliabilities) and a results narrative; Ch. 1–3 (intro, lit, model, hypotheses) are already written. Mediation/hypothesis testing is out of scope this term (advisor directive) and noted as future research.

## Bottom line

The hard intellectual work — model, hypotheses, instrument, peer review — is done. The next two weeks are execution and analysis. The single highest-leverage action is getting the survey live today. Start with TODAY item 1.