# Project Update — One Page

To: Prof. Dr. Juan Rey | From: Yasir A. Malik (PID 1687105) | Date: June 21, 2026

Re: Peer review of the survey instrument; instrument fielding this week per your timeline

Where things stand. The full measurement instrument (eleven constructs, five items each) completed an informal peer review by an audit-experienced reviewer this week. I have analyzed every comment, applied the validity-improving changes, and documented reasoned decisions where I held a design choice. The instrument is now v2 and is being loaded into Qualtrics to field this week, on the day-by-day schedule below. The eleven constructs, the five-items-per-construct structure, and the sixteen hypotheses are unchanged, so the exploratory-factor-analysis and mediation plan is fully preserved.

What the review changed (all wording, coverage, or controls — no construct redefined):

Eight items reworded for clarity and fairness to internal auditors — e.g., the independent-review item now reads "Reviewers challenge whether my judgments rely too heavily on prior-year audit conclusions"; the regulatory item now names PCAOB, AICPA, IIA, and COSO; the incentives reverse-item was rewritten so it measures the firm's incentive system rather than universal budget pressure (a contamination the reviewer correctly flagged).

Two controls added — a context item on whether the audit team actually has access to prior-year files (the anchoring premise assumes exposure to the anchor), and a split of audit experience into external vs internal years (internal auditors often have prior external experience).

Respondent-facing items: 71 → 73.

Reasoned decisions I am flagging for you:

5-point vs 7-point Likert. The reviewer asked about 7-point. I recommend keeping 5-point — the measurement literature shows reliability/validity gains plateau by ~7 points and that 5- and 7-point scales perform comparably (Preston & Colman, 2000, Acta Psychologica; Dawes, 2008, Int. J. Market Research), while 5-point reduces fatigue across 55 items and renders better on mobile. This is reversible before launch if you prefer 7-point — please let me know.

Regulatory + Professional Guidance as one construct. The reviewer asked whether to split it. I am keeping it combined (both operate through the same accountability/System-2 mechanism), but the EFA will test its dimensionality empirically — if the items split into two factors, I will report it and revise the model with your sign-off.

Scope and IRB. Every change is wording, coverage, or a control; none alters what a construct measures, so none is a substantive IRB change. Monday's item-by-item reconciliation against the IRB-approved instrument will confirm this; anything judged substantive halts and escalates to you and the IRB before fielding.

Plan this week (day by day).

Mon Jun 22 — Reconcile v2 against the IRB-approved instrument; review pilot feedback.

Tue Jun 23 — Build + preview-test + publish in Qualtrics; send the informed-pilot link to 6–10 eligible auditors that evening.

Wed Jun 24 — Informed pilot open; collect feedback.

Thu Jun 25 — Close pilot (≥6 completions); apply wording-only fixes; verify the six pre-launch decision gates.

Fri Jun 26 — CloudResearch soft-launch — data collection begins.

Sun Jun 28 — Submit Weekly Update W07 with data-collection progress.

Full detail (the verbatim review, the point-by-point response, and the v2 instrument) is on the project repository:

https://github.com/AuditingAI/Profile/tree/claude/scholar-links-review-Plgk6/dba/04_Peer_Review

— Yasir A. Malik | PID 1687105 | FIU DBA Cohort 7.16 | IRB-25-0462