# Catch-Up Email to Dr. Rey (paste, attach the ZIP, send)

Subject: DBA project — re-baseline + READY packet for instrument and pilot

Dr. Rey,

Two weeks have passed since your June 1 note, and I owe you a clean status. The READY packet I had prepared for that conversation — the revised paper, the informed-pilot protocol, the CloudResearch and MTurk launch drafts, the recruiting checklist, and the LinkedIn outreach copy — has been on the project repository the whole time. I did not move forward in the window I should have, and I'm restarting deliberately tonight.

Where things stand, honestly:

Paper: v4.2 complete. Chapters 2 and 3 expanded per our last call, model figure embedded in Chapter 3, instrument in Appendix A. No changes needed before the pilot.

Instrument in Qualtrics: not yet built. This is what I am committing to finish this week.

Informed pilot protocol: READY (6–10 auditor target, feedback form, revision log, decision rules).

Recruiting platforms: CloudResearch and MTurk launch drafts both READY; CloudResearch is the primary channel, MTurk the backup.

LinkedIn outreach copy: three IRB-aligned templates drafted, awaiting your sign-off.

IRB: Protocol IRB-25-0462 active through September 2030; the Topaz PI-change amendment is the only follow-up.

My commitment for this week (June 15–21, Week 5):

| By | Deliverable |
| --- | --- |
| Tuesday, June 16 | Appendix A items reconciled against the IRB-approved instrument; reconciled item list filed in the Revision Log |
| Thursday, June 18 | Qualtrics survey built, preview-tested (eligible + screen-out paths), anonymous link ready |
| Friday, June 19 | Brief Zoom with you to walk the build for face-validity sign-off + LinkedIn copy sign-off + CloudResearch compensation amount |
| Saturday, June 20 | Pilot invitations sent to 6–10 LinkedIn audit contacts |
| Wed, June 24 | Pilot responses closed; revisions logged and applied within IRB scope |
| Mon, June 29 | CloudResearch soft-launch (10–15 responses) |

This puts the full CloudResearch data window in the first half of July, which preserves the July 19 manuscript milestone.

All supporting materials are attached as a single ZIP, and everything also lives on the project branch:

https://github.com/AuditingAI/Profile/tree/claude/scholar-links-review-Plgk6/dba

I'd value a 20-minute Zoom this week at any window that suits you, on or before Friday. If you can reply with a time, I will be there.

Thank you for your patience.

Sincerely,

Yasir

Yasir A. Malik

PID 1687105 | FIU DBA Cohort 7.16

# What's attached (the ZIP — same 10 files from the June 1 READY packet)

| # | File | Purpose |
| --- | --- | --- |
| 1 | Research_Paper_YMalik_v4.docx | The paper (v4.2) — Ch. 2, Ch. 3, figure, Appendix A instrument |
| 2 | ALL_IN_ONE_DBA_Package_v3.docx | Single navigable consolidation of everything |
| 3 | 2026-06-14_Catchup_Status_to_Rey.docx | This message + the commitment table |
| 4 | Weekly_Update_W05_2026-06-14.docx | Current week status update (Week 5 of 9) |
| 5 | Data_Collection_Readiness.docx | Stage-by-stage readiness with traffic-light view |
| 6 | LinkedIn_Outreach_Pack.docx | 3 IRB-aligned LinkedIn templates |
| 7 | YMalik_Informed_Pilot_Protocol_READY_2026-06-01.docx | Pilot protocol + decision rules |
| 8 | YMalik_Pilot_Feedback_Form_and_Revision_Log_READY_2026-06-01.xlsx | 4-tab pilot workbook |
| 9 | YMalik_CloudResearch_Launch_Draft_READY_2026-06-01.docx | Primary route |
| 10 | YMalik_MTurk_Backup_Launch_Draft_READY_2026-06-01.docx | Backup route |
| 11 | YMalik_Recruiting_Launch_Checklist_READY_2026-06-01.xlsx | 5 gate tabs |

# Honest note to self — why this gap happened and what I'm changing

This block is for me, not for Dr. Rey. Two weeks slipped because the work moved from "writing" (which I can sit and do) to "platform builds + outbound conversations" (which require initiating). The dashboard, the Build & Launch Guide, and the Pilot Run Status table are all designed to remove that friction — but they only help if I open them.

Mechanism to keep this from happening again, starting tonight:

Every morning this week, open dba/dashboard.html first. Move one checkbox.

Time-box the Qualtrics build to 90-minute focused sessions (Mon, Tue, Wed mornings). Do not seek to "finish in one sitting."

End-of-day: commit and push whatever state the build is in, even if incomplete. Visible progress on the repo is forcing function.

If I miss a daily checkbox by 24 hours, send Dr. Rey a one-line text update — no excuses, just the date and the next deliverable.