# Data Collection Readiness — Summary for Advisor

# Data Collection Readiness Checklist

Project: Mitigating Anchoring Bias in Long-Term Auditor Engagements

Author: Yasir A. Malik (PID 1687105) — FIU DBA Cohort 7.16

Advisor: Prof. Dr. Juan Rey

Compiled: June 1, 2026 — updated with 03_Recruitment_and_Pilot READY packet

Owner of unchecked items: Yasir (this is the work that must happen before pilot launch)

## Stage 0 — Ethics & Regulatory 🟢 COMPLETE

✅ IRB approval — FIU IRB Protocol IRB-25-0462, approved September 2, 2025, effective through September 2, 2030 (5-year exempt status)

✅ Informed consent letter — IRB-approved Informational Letter presented as the first screen of the survey before any item

✅ Compensation structure — fixed, Florida-compliant amount paid on submission; no incentive tied to answer content

⏳ IRB PI-change amendment — to be filed in Topaz this week per Weekly Update W01 v2

✅ Data-handling protocol — anonymous collection via FIU Qualtrics, IP retention disabled, FIU-secured storage, access limited to investigator and advisor

## Stage 1 — Instrument 🟡 FINAL BUILD IN PROGRESS

✅ Constructs defined — 11 constructs operationalized in Research_Paper_YMalik_v4.docx §§ 2.4–2.13 (8 IVs + 2 mediators + 1 DV)

✅ Items drafted — 5 items × 11 constructs = 55 construct items + 12 demographics, in v4 Appendix A

✅ Reverse-coded items — one reverse-coded item per construct, embedded

✅ Attention checks — two embedded ("select Disagree", "select Agree")

⏳ Reconciled against IRB-approved instrument — Appendix A is a draft for reconciliation; the IRB-approved instrument (Updated Measurement Instrument – Malik, Y.docx) governs where they differ. ACTION: open both side-by-side, confirm wording matches, log any differences as either (a) non-substantive or (b) requiring a Topaz amendment.

⏳ Loaded into Qualtrics — final reconciled items entered into FIU Qualtrics. ACTION: complete before today's meeting if possible; if not, screen-share whatever state the build is in.

⏳ Survey logic — consent block → demographics → randomized construct blocks → debrief → submission confirmation. ACTION: verify in Qualtrics.

⏳ Face-validity walk-through with Dr. Rey — this is the explicit ask from his 2026-06-01 email.

## Stage 2 — Informed Pilot 🟢 READY PACKET COMPLETE (awaits Stage 1 closure)

📦 READY packet filed at dba/03_Recruitment_and_Pilot/ as of 2026-06-01:

| Artifact | Status | Path |
| --- | --- | --- |
| Informed Pilot Protocol | ✅ READY | 03_Recruitment_and_Pilot/YMalik_Informed_Pilot_Protocol_READY_2026-06-01.docx |
| Pilot Feedback Form + Revision Log (xlsx, 4 tabs) | ✅ READY | 03_Recruitment_and_Pilot/YMalik_Pilot_Feedback_Form_and_Revision_Log_READY_2026-06-01.xlsx |
| CloudResearch Launch Draft | ✅ READY | 03_Recruitment_and_Pilot/YMalik_CloudResearch_Launch_Draft_READY_2026-06-01.docx |
| MTurk Backup Launch Draft | ✅ READY | 03_Recruitment_and_Pilot/YMalik_MTurk_Backup_Launch_Draft_READY_2026-06-01.docx |
| Recruiting Launch Checklist | ⚠️ MISSING — referenced in README but not yet in repo | (YMalik_Recruiting_Launch_Checklist_READY_2026-06-01.xlsx to be added) |

Pilot protocol (confirmed in READY packet):

✅ Target n = 6–10 eligible auditors (face-validity / clarity / timing / technical pilot, not statistical)

✅ Eligibility = survey eligibility — age 18+, current/recent auditor, ≥2 yrs experience, recurring/long-term engagement exposure

✅ Boundaries — no employer/client/account-level/confidential data requested in pilot or full survey

✅ Scope discipline — current model only (TA, RA, AT, SAP, FR, IR, RPG, PMI → AJQ/APR → RAB); AI/LLM constructs reserved for future research, not in this data collection

✅ Decision rules — clarity < 4/5 triggers wording revision; construct-fit < 4/5 triggers advisor review; IRB-scope-affecting feedback halts and triggers Topaz amendment

✅ Feedback instrument — 10 questions (PF1–PF10): clarity of consent, eligibility, audit-language fit, length, technical flow, confusing items, redundancy, sensitive-data flag, completion time, open comments

✅ Participant log structure — 10-row template, anonymous Pilot IDs only (P01–P10); no employer/client names recorded

✅ Revision log structure — 20-row template, severity-tagged, advisor/IRB-review flag column

✅ Decision summary — 6 launch-gating criteria pre-defined (size, timing, no sensitive data, scope, revision boundary, launch decision)

Pre-launch tasks (remaining):

⏳ Pilot recipient identification — 6–10 LinkedIn audit contacts who meet eligibility

⏳ Pilot invitation copy — short, friendly, IRB-aligned, time estimate (~18 min)

⏳ Qualtrics preview testing — both eligible and screen-out paths

⏳ Pilot link distribution after face-validity sign-off

## Stage 3 — Recruiting Platforms 🟢 LAUNCH DRAFTS READY (sequencing locked)

### Sequencing rule (per CloudResearch READY draft)

CloudResearch first, because (a) Dr. Rey explicitly identified recruiting platforms in his 2026-06-01 message and (b) the IRB file references CloudResearch for subject recruitment. MTurk second, only if CloudResearch yield or quality is insufficient after the initial window.

### 3a — CloudResearch (primary) ✅ Launch draft READY

✅ Study title — "Auditors' Professional Judgments and Audit Work Practices"

✅ Short description — 15-20 min anonymous academic survey

✅ Eligibility filters — age 18+, current/recent auditor, ≥2 yrs experience, recurring-engagement exposure

✅ Compensation — fixed platform amount, value pending advisor confirmation

✅ Soft-launch protocol — 10-15 responses first; review eligibility pass rate, attention checks, completion time, duplicate risk, export integrity before full launch

✅ Quality filters — duplicate prevention, suspicious-activity controls, page-timing flags, 2-of-3 attention-check exclusion rule

✅ Target — n = 60-80 valid responses after cleaning

✅ Do-not-add boundaries — no AI/LLM items in this survey, no employer/client/confidential/sensitive data, no scope-affecting changes without advisor/IRB

⏳ Account setup with researcher credentials + IRB on file

⏳ Project creation in CloudResearch dashboard

⏳ Compensation amount confirmation with Dr. Rey

### 3b — MTurk (backup) ✅ Launch draft READY

✅ HIT title + description + eligibility + instructions + qualifications + compensation language — drafted

✅ Use condition — backup or second channel only if CloudResearch insufficient

✅ Quality review — screen-out rate, eligibility fit, attention checks, page timing, straight-line detection, duplicate exclusion

✅ Boundary — same model, no AI/LLM scope creep, no IRB-scope changes

✅ Quality threshold — 95%+ approval, 100+ approved HITs (if consistent with platform plan)

### 3c — LinkedIn (parallel channel) ✅ Outreach copy READY (awaiting sign-off)

✅ Outreach copy — three IRB-aligned templates in LinkedIn_Outreach_Pack.docx

⏳ Advisor sign-off on copy — explicit ask in today's meeting

⏳ Outreach log spreadsheet — IRB-compliant fields only (no identity-to-submission linkage)

### 3d — IIA chapter referrals (backfill) ⏳ Pending

⏳ Identify South Florida / Miami chapter contacts

⏳ Email-introduction copy + advisor sign-off

## Stage 4 — Analysis Readiness 🟢 PIPELINE SPECIFIED

✅ Analysis plan documented — Research_Paper_YMalik_v4.docx § 4.4 (cleaning → descriptives → reliability α ≥ .70 → EFA with PAF + varimax + KMO + Bartlett + parallel analysis → correlations → regression → PROCESS Model 4 mediation, 5,000 bootstraps)

⏳ Software access — SPSS + PROCESS macro confirmed available via FIU

⏳ EFA decision rules pre-specified — Kaiser–Guttman + scree + parallel analysis convergence; minimum factor loading 0.40; cross-loading threshold 0.30

⏳ Sample-size monitoring rule — close collection at n = 60 minimum / 80 target / hard stop at 100

## What's actually blocking the pilot, in one sentence

Once the instrument is reconciled with the IRB-approved version, loaded into Qualtrics, and Dr. Rey has signed off on its face validity and the LinkedIn outreach copy, the pilot launches — and the pilot protocol, feedback form, revision log, and both recruiting-platform drafts are already READY in dba/03_Recruitment_and_Pilot/.

## Status traffic light, as of 2026-06-01 (after READY packet)

| Stage | Status | Change since v1 |
| --- | --- | --- |
| 0 — Ethics / IRB | 🟢 Complete | — |
| 1 — Instrument | 🟡 Draft complete; Qualtrics build + face-validity walkthrough pending | — |
| 2 — Informed pilot | 🟢 READY packet complete (was 🟡) | ⬆️ Protocol, feedback form, revision log, decision rules all filed |
| 3 — Recruiting platforms | 🟢 CloudResearch + MTurk drafts READY (was 🔴) | ⬆️ Launch drafts filed; sequencing locked |
| 4 — Analysis pipeline | 🟢 Plan documented | — |

Net read for the advisor: project moved from "paper-only" to "READY-to-launch" in one cycle. Three remaining blockers are all addressable in one meeting (Qualtrics build, face-validity sign-off, LinkedIn copy sign-off). After that, soft-launch can begin within the same week.