# Status Email to Dr. Rey — 20 Responses, Recruitment Constraint, Plan to Deadline

From: ymali001@fiu.edu | Date: July 9, 2026

Purpose: honest status + three narrow, decision-ready questions (per Dr. Rey's guidance boundary). Not a review request.

## Email to send (copy-paste; keep or delete the [OPTIONAL] line)

Subject: Data Collection Status — 20 valid responses; recruitment constraint and plan to the July 19 deadline

>

Dr. Rey,

>

A transparent status update on data collection, with three specific questions at the end.

>

Status. The survey has been live on FIU Qualtrics since July 1 and is functioning correctly — screeners, embedded attention checks, and anonymity settings are all working. To date I have 20 valid responses. This is well short of the n = 100 target, and I want to explain why and show you my plan rather than let the number arrive without context.

>

The constraint. I want to be candid: I recently lost my job, which has made funding the paid recruitment panel (approximately $600–750 on Prolific for 100 auditor completes) infeasible this month. I pivoted to no-cost recruitment — LinkedIn posts and reshares across audit and accounting networks, professional WhatsApp groups, and direct outreach to audit contacts — which produced the responses collected so far. [OPTIONAL: I can commit roughly $100–200 to a partial Prolific batch this week, which at their fair-pay rate would add approximately 20–40 completes.]

>

What has been tried. CloudResearch's self-service panel was confirmed by their own support team as unable to reach verified audit professionals; their alternative (Managed Research) is a full-service engagement beyond my current means. A Prolific study is fully configured with US audit/finance prescreening and sits ready to fund. Free-channel outreach continues daily (LinkedIn, IIA/AICPA chapter contacts, FIU network).

>

My plan to protect the July 19 deadline. Continue the free-channel push through Sunday, July 13, then freeze the survey that evening and export. Run the data analysis per your Assignment 4 procedure — cleaning and exclusion log, descriptives and normality, EFA with principal axis factoring (both rotations run; Direct Oblimin reported), and reliabilities — on July 14–15. The manuscript's front half (Introduction through Methodology) is being assembled now since it does not depend on the data. The manuscript will be submitted on time on July 18–19; the only variable is the final sample size, which I will report transparently with its limitations.

>

My three questions:

>

1. Given this constraint, is proceeding with whatever sample I reach by July 13 acceptable — reporting the shortfall honestly as a limitation — or would you advise a different cutoff date within the deadline?

2. Is there a minimum n below which you would advise against running the EFA at all, versus running it and reporting the adequacy diagnostics (KMO, Bartlett's) exactly as they come out?

3. Does FIU or the DBA program have any participant pool, alumni distribution channel, or similar mechanism I could use this week at no cost to reach audit professionals?

>

Thank you for the direction throughout — the guided EFA assignment has the analysis fully mapped and ready to execute the moment collection closes.

>

Best regards,

Yasir A. Malik

PID 1687105 | FIU DBA Cohort 7.16

## Why the email is built this way

Leads with the number (20) — he learns it from you, framed, not from a late discovery.

One sentence on the job loss — context, not excuse; immediately followed by what you did about it.

Shows what was tried — satisfies his standing expectation ("show what was tried") and demonstrates the shortfall is a resource constraint, not low effort.

Commits to the deadline unconditionally — the manuscript ships Jul 18–19; only n varies. This is the single most important sentence for how the situation reads.

Three narrow questions — each answerable in one line, consistent with his "specific methodological questions in advance" boundary. Question 2 is genuinely methodological (EFA sample adequacy); questions 1 and 3 are logistics he can answer instantly.

No extension request — the course deadline is fixed; asking would read poorly. The ask is how to execute within it.